## FIELDS_TIMELINE
| Name of the project: |  |  | Erasmus+ FIELDS Blueprint
PROJECT TIMETABLE
[5 empty] | January | [11 empty] | January | [11 empty] | January | [11 empty] | January
|  |  |  | MONTHS | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 | M13 | M14 | M15 | M16 | M17 | M18 | M19 | M20 | M21 | M22 | M23 | M24 | M25 | M26 | M27 | M28 | M29 | M30 | M31 | M32 | M33 | M34 | M35 | M36 | M37 | M38 | M39 | M40 | M41 | M42 | M43 | M44 | M45 | M46 | M47 | M48
| Project activity* | Leader | Partners Involved
1 | Skills needs identification | ISEKI | bar: January M1 to January M15
1.1 | State of the Art | UNITO | All partners |  | January M6: D1.2; January M12: D1.1
1.2 | Stakeholders strategical mapping and mobilisation | LLL-P |  |  | January M6: D1.3
1.3 | Country and EU focus groups | ISEKI |  |  | January M7: D1.4; January M12: D1.5
1.4 | Bottom-up surveys | ICOS |  |  | January M12: D1.6; January M16: D1.7
1.5 | Future trends analysis | WUR |  |  | January M16: D1.8
2 | Priorities and strategy design | CONFAGRI | bar: January M12 to January M48
2.1 | Analysis of skill gaps and new profiles creation | AC3A |  |  | January M23: D2.1
2.2 | Profiles prioritisation | Confagri PT - FIELDS |  |  | January M24: D2.2
2.3 | European Strategy formulation | WUR - FIELDS |  |  | January M24: D2.3; January M45: D2.3
2.4 | Roadmap formulation and refining | CONFAGRI - FIELDS |  |  | January M33: D2.4; January M47: D2.4
2.5 | Transferability framework | LLL-P - FIELDS |  |  | January M30: D2.5
3 | New tools and training design | UNITO - FIELDS | bar: January M4 to January M44
3.1 | Methodology definition | UNITO |  |  | January M26: D3.1
3.2 | Curricula design | ICOS - FIELDS |  |  | January M30: D3.2
3.3 | Apprenticeship scheme | AERES - FIELDS |  |  | January M42: D3.3
3.4 | Training content creation and new tools | UCLM - FIELDS |  |  | January M38: D3.4
3.5 | Train the trainers materials and tools | AP - FIELDS |  |  | January M38: D3.5
4 | Implementation and pilots | AERES - FIELDS
4.1 | Setup and running of Train-the-trainer pilot | AP - FIELDS |  |  | January M41: D4.1
4.2 | Setup and running of Training pilot | AERES - FIELDS |  |  | January M46: D4.2
4.3 | Map creation, update and use | UNITO |  |  | January M12: D4.3; January M48: D4.3
4.4 | Translation | CONFAGRI - FIELDS |  |  | January M48: D4.4
5 | Sustainable action plan | ICOS - FIELDS | bar: January M7 to January M48
5.1 | National and EU regulatory frameworks | Confagri PT - FIELDS |  |  | January M25: D5.1
5.2 | Funding opportunities | LLL-P - FIELDS |  |  | January M24: D5.2
5.3 | Platform governance | PA - FIELDS |  |  | January M45: D5.3
5.4 | Stakeholders future engagement | ISEKI - FIELDS |  |  | January M45: D5.4
6 | Quality assessment | CERTH - FIELDS
6.1 | Quality plan | CERTH - FIELDS |  |  | January M4: D6.1; January M6: D6.2
6.2 | Quality assessment | EFB - FIELDS |  |  | January M48: D6.3
6.3 | External Expert review | EFB - FIELDS |  |  | January M33: D6.4; January M48: D6.4
6.4 | EQAVET assessment | INFOR - FIELDS |  |  | January M46: D6.5
7 | Engagement and dissemination | ACTIA - FIELDS
7.1 | Dissemination plan | LVA - FIELDS |  |  | January M9: D7.1
7.2 | Communication and dissemination campaign | FIAB - FIELDS |  |  | January M6: D7.2&7.3; January M48: D7.4
8 | Project management | UNITO - FIELDS
8.1 | Decision making and internal communication | UNITO |  |  | January M3: D8.2; January M6: D8.1
8.2 | Administrative and financial management | UNITO
8.3 | Progress monitoring and risk management | UNITO |  |  | January M1: D8.3; January M13: D8.3; January M25: D8.3; January M37: D8.3; January M48: D8.3
M1: Coordination meetings | bar: January M1; January M6; January M13; January M18; January M25; January M30; January M37; January M42; January M46; January M48
Please insert rows as needed
*Project activity types:
|  |  |  | An | January M1: - PROJECT MANAGEMENT AND IMPLEMENTATION ACTIVITIES
|  |  |  | On/An | January M1: - INTELLECTUAL OUTPUTS/ACTIVITIES
|  |  |  | Mn | January M1: - TRANSNATIONAL PROJECT MEETINGS
|  |  |  | En | January M1: - MULTIPLIER EVENTS
|  |  |  | Cn | January M1: - LEARNING/TEACHING/TRAINING ACTIVITIES
|  |  |  | n | January M1: - number of the activity
Please enter all main project activities and meetings, intellectual outputs and related activities, multiplier events and training/teaching/learning activities. Use the reference numbers as they appear in the application form. Where no numbers exist in the application form (i.e. for activities included in project management and implementation), use reference numbers A1, A2 etc. For each activity, meeting or event, indicate the month(s) in which they will be produced/take place by colouring the corresponding cells.