## Slide 1: WP2 Priorities and Strategy Design
Daniel Rossi, Delegate R&I
Camilla Tomao, Claudio Carpineti, Elisabetta Pierantoni
CONFAGRICOLTURA WP2 Leader
30-31st May 2022
Ania, France
FIELDS – Blueprint 612664 – 1/1/20-41/12/24

## Slide 2
WP2 Priorities and Strategy Design
WP Start/End date: M12-M48
Partners involved: ALL

## Slide 3
Aim: Strategy and Implementation Plans
Main Objectives:
Perform an analysis of the skill gaps in agriculture and forestry related to three areas: Sustainability, Bio-economy and Digitalization considering also the soft skills
Compare and prioritize the skills in these domains
Develop a general EU strategy to transfer these skills to agriculture and related sectors
Develop 7 specific National Roadmaps NRM (Spain, France, Italy, Austria, The Netherlands, Finland, Ireland)
Mobilize knowledge around EU with a transferability framework by matching the National Roadmaps NRM with EU tools (CEDEFOP, ESCO, ECVET, ECTS)

## Slide 4
Tasks
Completed by M24 – December 2021
T2.1 Analysis of skill gaps and new profiles creation (M12-M20)
Task Leader AC3A, Partner UNITO, CONFAGRI, ISEKI, ICOS, AERES, AP, UHOH, CERTH, ACTIA, GAIA, CONFAGRI PT, SCOOP, GSZ, LVA, UCLM, AC3A, FIAB, FDE, FENACORE, INFOR, LLL-P, ANIA, PlanetETP, EFB, PA, FJ-BLT, AFVET, CEPI, FJ-BLT
Deliverable: List of newly identified occupational profiles and their description of skills, competences, knowledge and qualifications.
T2.2 Profiles prioritization (M14-M21)
Task Leader CONFAGRI PT, Partner UNITO, CONFAGRI, WUR, ISEKI, ICOS, AERES, AP, UHOH, SCOOP, GZS, UCLM, AC3A, FIAB, INFOR, ANIA, EFB, FJ-BLT, CEPI
Deliverable: 10 new occupational profiles standardized for transferability.

## Slide 5
Tasks
Ongoing – end of the project M48
T2.3 European Strategy formulation (M12-M48)
Task Leader WUR, Partner ALL
Deliverable: Draft submitted in M24 (December 2021) Intermediate report towards Deliverable D3.2 (European Strategy) of the FIELDS project (Month 45, September 2023) – link with Pact for skills

## Slide 6
Tasks
Ongoing – end of the project M48
T2.4 Roadmap formulation and refining (M25-48)
Task Leader CONFAGRI, Partner ALL
Currently ongoing National Working Meetings in the 7 target countries
Deliverable:
Draft report on 7 National Roadmaps to be submitted within M33 (September 2022).
Deliverable D2.4 due date M45 (September 2023).

## Slide 7
Tasks
Ongoing
T2.5 Transferability framework (Started M23 November 2021)
Task Leader LLL-P, Partner INFOR, AERES, AP, UNITO, EfVET
Deliverable: Report. Country guidelines and references to allow transferability of curricula within Europe.

## Slide 8
THANK YOU!
Daniel Rossi
d.rossi@confagricoltura.it;
Camilla Tomao
tomao@enapra.it
Claudio Carpineti
claudio.carpineti@gmail.com