## Slide 1: FIEDS Virtual meeting – 28.05.2020
WP7 – Dissemination and communication
ACTIA - Christophe Cotillon - c.cotillon@actia-asso.eu ACTIA – Gemma Cornuau – g.cornuau@actia-asso.eu LVA – Julian Drausinger – julian.drausinger@lva.at FIAB – Conchà Avila – c.avila@fiab.es

## Slide 2: WP7 Info
WP Start/end date: M1-M48
Lead by ACTIA and all partners are involved
WP7 aims to ensure to reach the largest possible target audience while advertising the project results
The network of the associated partners (EFFAT, BIC) and of the entity supporting the project (COPA-COGECA) will also be used for a wider reach of farmer association and cooperatives
A dissemination plan will be developed by LVA to support the outreach of the project to the target audiences in the participating countries and following succesful validation to other countries.

## Slide 3
T7.1 Dissemination plan
Duration: M1-M9 Leader: LVA (60 days)
Involved: CONFAGRI (20 days), UNITO (30 days), FIAB (18 days), ACTIA (18 days)

## Slide 4: T7.1 Dissemination plan
The task 7.1. aims to define the overall communication and dissemination plan
Deliverable 7.1: Dissemination plan, M9
  to be developed by LVA in collaboration with FIAB, CONFAGRI, ACTIA and UNITO
  to be validated by all project partners during a project meeting
  common goal: communicating and disseminating the project’s objectives outputs, interim and final results
The main content of dissemination plan is to develop a strategy to:
o outline key dates/ times of dissemination activities
around the dates of deliverables of the WPs.
based
o identify most efficient methods to ensure project results and strategies are communicated and adopted by EU policy makers and into existing and future legislation at EU and Member states

## Slide 5
T7.2 Communication and dissemination campaign
Duration: M1-M48 Leader: FIAB (155 days) Involved: All partners

## Slide 6: T7.2 Communication and dissemination campaign
Some of the actions will be:
Newsletters (written by FIAB)
7 Communication workshops (LVA, AERES, CONFAGRI, ACTIA, FIAB, ICOS, PA)
Dissemination to media via press releases and articles
FDE will disseminate the project results through the National
Food and Drink Industry Federations, and the National Food Technology Platforms to the Food Industry
Videos of interviews (during VET training)
Social media (instagram, to impact learners population by VET and training providers)
Promotion of agriculture careers and gender equality (through the project’s events)
Google AdWords campaign will be issued when content is available to impact the target groups
A final conference will be organised in Brussels
the training

## Slide 7: T7.2 Communication and dissemination campaign
Deliverables:
D7.2: Public Website (M3)
  UNITO will design and develop a project website, which will be available in the 10 project partners’ languages
D7.3: Project leaflet and poster (M6)
  A project logo has been developped by ACTIA.
  A project leaflet will be developed by UNITO.
  Partners will be responsible for the translation and printing in the corresponding languages
D7.4: Report on dissemination action (M48)
  The dissemination actions will be monitored by FIAB and the result of the communication will be updated at the yearly meeting and during the virtual meetings.

## Slide 8
Q&A