## Slide 1: FIELDS WP8 - Project Management
Francesca Sanna, Project Manager
Remigio Berruto, Coordinator
5th Project Partnering Meeting – Paris, France
30-31 May 2022

## Slide 2: WP8 - Project Management (UNITO) M1-M48
Task 8.1: Decision making and internal communication, M1-M48
D8.1: Consortium agreement (M1)
Task 8.2: Administrative and financial management, M1-M48
D8.2: Intranet (M1)
Task 8.3: Progress monitoring and risk management, M1-M48
D8.3: Progress reports M1, M13, M25, M37, M48

## Slide 3: WP8 - Project Management (UNITO)
Management portal / official website
Technical and Financial reporting
Rescheduled activities
Monitoring of the activities and communications among partners
Future activities and next meetings
Remigio Berruto /Francesca Sanna (UNITO)

## Slide 4: WP8 - Project Management (UNITO)
Change of the Coordinator:
Remigio Berruto instead of Patrizia Busato
Amendment: New affiliated entity: Asociación Galega de Cooperativas Agroalimentarias – AGACA
Linked to Cooperativas Agro-alimentarias de España- SCOOP
Task 8.1: Decision making and internal communication, M1-M48
Entered into force the 1st July 2021

## Slide 5: Activities and deliverable progress
25 Deliverables submitted, 9 in progress

## Slide 6: WP8 - Project Management (UNITO)
Progress report M1 submitted the 14/02/2020 (after Kick-off meeting)
Technical-progress report M13 submitted the 05/02/21
Interim report in M25 with pre-financing payment, submitted the 05/03/2022
Task 8.3: Progress report, M1-M48

## Slide 7: FIELDS progress report, EACEA
Submitted the 05/03/2022
Midterm progress report with pre-financial
Review meeting with EACEA and representative of DG GROW/DG EMPL
05/04/2022
Evaluation results
Task 8.2: Administrative and financial management, M1-M48

## Slide 8: WP8 - Project Management (UNITO)
Task 8.2: Administrative and financial management, M1-M48
Webinar on financial issues, use of timesheet template, deadlines etc. – Q/A
Organised in Dicember, before the interim report in M25 with pre-financing payment
https://drive.google.com/file/d/1F2dJ_PAjx4dllZ-S0zhPBhH0w16TMlug/view?usp=sharing

## Slide 9: FIELDS rescheduling activities
New scheduled activities, including the reallocation of the days not spent in the first period, in order to complete some tasks as soon as possible considering the delays occurred during last year.
New Gantt chart

## Slide 10: FIELDS rescheduling activities

## Slide 11: WP8 - Project Management (UNITO)
Task 8.2: Administrative and financial management, M1-M48
http://www.erasmus-fields.eu/management/
D8.2: Intranet (M1)

## Slide 12: Templates
Task 8.2: Administrative and financial management, M1-M48

## Slide 13: WP8 - Project Management (UNITO)
Official website / Social media

## Slide 14: Dissemination
Dissemination on WP1 outcomes
Two articles in preparation (ISEKI), to be submitted in the special issue "Sustainable Food System in the European Union"
Tentative titles:
1. Skill needs for sustainable agri-food and forestry sectors (I): assessment through European and National Focus Groups 2. Skill needs for sustainable agri-food and forestry sectors (II): insights of a European Survey

## Slide 15: WP8 - Project Management (UNITO)
Task 8.3: Progress monitoring and risk management, M1-M48
Meeting | Date | Place | Host
Kick-off | M1 | Turin, Italy | UNITO
Management Meeting 1 (MM1) | M13 | Vienna, Austria | ISEKI/LVA
MM2 | M25 | Paris | ANIA
MM3 | M37 | Wageningen, Netherlands | WUR
MM4 | M45 | FIAB | Spain
Final conference in Brussels | M48 | FDE | Brussels
In addition, the HSC will meet also on M6, M18, M31 and M42, with only representatives of the WP leaders. Other partners are welcome to participate.
In addition, a virtual conference call will be organised every 2 months to closely monitor the evolution of tasks and deliverables of the project

## Slide 16: Next meetings - calendar
FIELDS MEETINGS 2021 |  |  |  |  | 
Day | hour start | hour End | Who | Zoom link | Notes
16/09/2021 | 14:30 | 15:30 | Working meeting |  | 
23/09/2021 | 14:30 | 15:30 | HSC meeting | https://us02web.zoom.us/j/82339687793 | 
30/09/2021 | 14:30 | 15:30 | Working meeting |  | 
14/10/2021 | 14:30 | 15:30 | Working meeting |  | 
28/10/2021 | 14:30 | 15:30 | Working meeting |  | 
11/11/2021 | 14:30 | 15:30 | Working meeting |  | 
18/11/2021 | 14:30 | 15:30 | HSC meeting | https://us02web.zoom.us/j/82339687793 | 
25/11/2021 | 14:30 | 15:30 | Working meeting |  | 
09/12/2021 | 14:30 | 15:30 | Working meeting |  | 
20/01/2022 | 14:30 | 15:30 | HSC meeting |  | 
17/03/2022 | 14:30 | 15:30 | HSC meeting | https://us02web.zoom.us/j/82339687793 | 
TBD |  |  | Working meeting |  | 

## Slide 17
Questions and comments?
Conclusion and greetings

## Slide 18: Thank you for your attention!
Francesca Sanna, FIELDS project manager
francesca.sanna@unito.it