## Slide 1: FIELDS project meeting
Francesca Sanna, Project Manager
Remigio Berruto, Coordinator
5th Partnering Meeting – Paris, France
30-31 May 2022

## Slide 2: Agenda
Day 1 | Project results & Future activities | Contributors
13:30 | Registration and Welcome coffee | 
14:05 | Greetings | Remigio Berruto, Francesca Sanna (UNITO) Françoise Gorga ANIA
14:05 | WP1 - Skills needs identification (ISEKI) | Luis Mayor / Ana Ramalho (ISEKI)
14:20 | WP2 – Priorities and strategy design (CONFAGRI) Task 2.1: Analysis of skill gaps and new profiles creation (AC3A) Task 2.2: Profiles prioritization (Confagri PT) Task 2.3: European strategy formulation (WUR) Task 2.4 Roadmap formulation and refining (CONFAGRI) Task 2.5 Transferability framework (LLL-P) | Daniele Rossi / Camilla Tomao Alexandre Morin (AC3A) Domingos Godinho (Confagri PT) Jacques Trienekens (WUR) C. Tomao (CONFAGRI) Erika Somlyay / Pauline Boivin (LLL-P)
15:00 | WP2 – Questions and Answers (Q/A) | 

## Slide 3: Agenda
Day 1 | Project results & Future activities | Contributors
15:15 | WP3 – New tools and training design (UNITO) Task 3.1: Methodology definition (UNITO), 10 min Task 3.2 Curricula design (ICOS) 10 min Task 3.3 Apprenticeship scheme (AERES) 5 min Task 3.4 Training content creation and new tools (UCLM), 5 min Task 3.5: Train the trainers’ materials and tools (AP) 5 min | R. Berruto, F. Sanna F. Sanna (UNITO) Billy Goodburn (ICOS) Marg Leijdens (AERES) Manuel Rodrigo / José Tarjuelo (UCLM) TBD (AP)
15:50 | WP3 – Q/A | 
16:00 | Coffee break | 

## Slide 4: Agenda
Day 1 | Project results & Future activities | Contributors
16:20 | WP4 - Implementation (AERES) Task 4.1 Setup and running of Train-the-trainer pilot (AP) Task 4.2 Setup and running of Training pilot (AERES) Task 4.3: Map creation, update and use (UNITO) | Marg Leijdens TBD M. Leijdens / J. Gundelach F. Sanna (UNITO)
16:45 | WP4 – Q/A | 
17:00 | Pact for Skills in Agri-food ecosystem Upskill and reskill people in the agri-food sector | Manuel Delgado (Copa-Cogeca) Jonas Lazaro-Mojica (FDE) Remigio Berruto (UNITO) Daniele Rossi (CONFAGRI)
17:30 | Questions and Comments | 
18:00 | Closing of day 1 | 
19:30 | Social dinner* | 

## Slide 5
Questions and comments
At the end of the WP session

## Slide 6: Activities and deliverable progress
25 Deliverables submitted, 9 in progress

## Slide 7: WP1 – Skills needs identification (ISEKI), M1-M15
Task 1.1: State of the Art (UNITO), M1-M6
  D1.1 Stakeholders strategic plans and analysis report, M1 – M6
  D1.2 Repository of previous projects, results and best practices, M1 – M6
Task 1.2: Stakeholders strategic mapping (LLL-P), M1- M6
  D1.3: VET list and classification (M6)
Task 1.3: Country and EU focus groups (ISEKI), M2-M9
  D1.4: Focus group guideline (M6)
  D1.5: Focus group analysis (M9)
Task 1.4: Bottom-up surveys (ICOS), M9-M12
  D1.6: Web-based questionnaire (M10)
  D1.7: Survey analysis (M12)
Task 1.5: Future trends analysis (WUR), M8-M15
  D1.8: Scenarios analysis (M15)
Luis Mayor, ISEKI-Food Association

## Slide 8: WP2 – Priorities and strategy design (CONFAGRI), M12-M48
Task 2.1: Analysis of skill gaps and new profiles creation (AC3A), M12-M15
Alexandre Morin (AC3A)
Task 2.2: Profiles prioritization (Confagri PT), M14-M18
Domingo Godinho (ConfagriPT)
Task 2.3: European strategy formulation (WUR), M12-M48
Jacques Trienekens (WUR)
Task 2.4: Roadmap formulation and refining (CONFAGRI), M17-M48
Camilla Tomao / Daniele Rossi (CONFAGRI)
Task 2.5: Transferability framework (LLL-P) M
Erika María Rodríguez Somlyay (LLL-P)

## Slide 9: WP3 – New tools and training design (UNITO) M4-M45
Task 3.1: Methodology definition (UNITO), M19-M27
D3.1: Training methodologies
Task 3.2: Curricula design (ICOS), M21-M30
D3.2: Curricula (M21)
Task 3.3: Apprenticeship scheme (AERES), M17-M42
D3.3: Apprenticeship scheme report (M42)
Task 3.4: Training content creation and new tools (UCLM), M20-M38
D3.4: Online training materials (M30)
Task 3.5: Train the trainers materials and tools (AP), M20-M38
D3.5: User guide for trainers and train the trainers’ session material (M30)

## Slide 10: 5th Project Meeting - Paris
Coffee break
See you at 16:20

## Slide 11: WP4 – Implementation (AERES)
Task 4.1 Setup and running of Train-the-trainer pilot (AP)
D4.1: Feedbacks from trainers (M41)
Task 4.2 Setup and running of Training pilot (AERES)
Marg Leijdens / Jan Gundelach
D4.2: Report and analysis of the training experimentation (M46)
Task 4.3: Map creation, update and use (UNITO), M4-M48
Francesca Sanna (UNITO)
D4.3: Online public platform and map (M12)

## Slide 12: Pact for Skills in Agri-food ecosystem
Manuel Delgado, Senior Policy Advisor, Employment & Social Affairs - COPA-COGECA
Jonas Lazaro-Mojica, Manager Food Policy, Science and R&D – FDE
Remigio Berruto, FIELDS Coordinator - UNITO
Daniele Rossi, Chairman Copa-Cogeca Research & Innovation – CONFAGRICOLTURA
Upskill and reskill people in the agri-food sector

## Slide 13
Francesca Sanna, FIELDS project manager
francesca.sanna@unito.it
Closing of day 1
See you tomorrow and have a nice evening!